## Gantt
ID | Uzdevums | Iepriekšējais | Ilgums | Izpildītājs | Marts |  |  |  | Aprīlis |  |  |  |  | Maijs
[5 empty] | 8.03-14.03 | 15.03-21.03 | 22.03-28.03 | 29.03-4.04 |  | 5.04-11.04 | 12.04-18.04 | 19.04-25.04 | 26.04-2.05 |  | 3.05-9.05 | 10.05-16.05 | 17.05-23.05 | 24.05
1 | Vides sagatavošana | - | 1 ned | visi
2 | Pamatu izveide | 1 | 1 ned | Artūrs +
3 | Projekta plānošana | 2 | 1 ned | visi
4 | Interfeisa izstrāde | 3 | 5 ned | visi
5 | Funkcionalitātes izstrāde | 4 | 5 ned | visi
6 | Testēšana un labojumi | 5 | 2 ned | visi
7 | Dokumentācijas izstrāde | 6 | 2 ned | visi
8 | Prezentācija | 7 | 1d | visi
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gantt izveide, DPD grafika izveide
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: pēc tam visi implementē savos datoros